## Sheet1
Impact
|  | Negligible | Minor | Moderate | Significant | Severe
Likelihood | Very likely | Low Med | Medium | Med High | High | High
| Likely | Low | Low Med | Medium | Med High | High
| Possible | Low | Low Med | Medium | Med High | Med High
| Unlikely | Low | Low Med | Low Med | Medium | Med High
| Very unlikely | Low | Low | Low Med | Medium | Medium
Number | Risk | Description | Likelihood | Impact | Matrix
1 | Illness | Injuring myself during the project may result in the inability or limit my work | Possible | Significant | Med High
2 | Inaccurate timing estimation | Not guaging the diificulty of a task appropriately may have a carry-on affect | Possible | Significant | Med High
3 | Added workload | Additional ideas being implemented can affect progress and other code where there are dependants | Possible | Minor | Low Med
4 | A layer of application breaks | Upon implementation or compiling of the project, elements or layers may cease to function or not work as intended | Possible | Significant | Med High
5 | Lack of skills | Not being able to complete an element or tasks due to a gap in knowledge | Possible | Minor | Low Med
6 | Injuries | Injuring myself during the project may result in the inability or limit my work | Possible | Significant | Med High
7 | Laptop breakdown | The laptop may malfunction during the project lossing progress and affect progress | Unlikely | Severe | Medium
8 | Loss of internet | The loss of internet would hinder the ability to research, colloborate and use materials | Unlikely | Severe | Med High
9 | Low productivity | Lack of productivity can affect the speed and progress in which I work at | Possible | Significant | Med High
10 | Uncooperative code | The code may not function as intended which result in delays or breakdown of components | Possible | Moderate | Medium
11 | Natural disasters | A natural disaster may occur causing damage to power-lines and/or infrastructure | Very Unlikely | Severe | Medium
12 | Unresponsive software | The software used may not work or not perform as it should resulting in delays as they will need to be resolved | Possible | Moderate | Medium
13 | Unsuitable product designed | The planned product may need changing during the project due to it not meeting the spec or it changing during the project | Possible | Moderate | Medium
14 | Linking of layers | The front and back end of the system do not link together as intended with integrated functionality | Possible | Minor | Low Med
15 | Deletion of files/log | My Jira and/or program coding is is deleted by accident or by a error | Unlikely | Severe | Med High